Flow  —  Product Roadmap

Full-stack build plan  •  29 June  →  31 July 2026

29 June 2026  •  React web  +  Flutter app  +  Laravel backend

Overview

This is not just one website — it is a full-stack product with three parts:

•  Flow-website — React web app (feature-rich UI, currently runs on mock data).

•  Flow_flutter — Flutter mobile/desktop port (near-parity, mock data).

•  Flow-backend — Laravel + PHP backend: migrations, models & controllers for users, channels, messages, documents, tasks, reactions, billing, marketplace and settings — plus a Gemini AI controller, broadcasting channels and Sanctum tokens.

Headline: the frontends are UI-complete but not connected to anything; the backend exists but is not wired up. The July arc turns a polished prototype into a real working app.

Progress so far  (baseline — Mon 29 June)

| Layer | State |
| --- | --- |
| React UI | ~95% built: chat, docs, Kanban, calendar, analytics, admin, marketplace, appearance, vault, huddle, whiteboard, Cmd+K palette, edit profile — all mock. |
| Flutter | Core + parity features ported (vault, landing, huddle, whiteboard, chat settings, notifications, palette, presence, analytics chart, edit profile, work modes) — mock. |
| Laravel backend | DB schema + models + controllers scaffolded; Gemini AI + realtime channels + token auth present; not connected to frontends. |
| Integration | None yet — frontends read local mock data. |

Weekly plan  (29 June → 31 July 2026)

Week 1  ·  Jun 29 – Jul 5   —   Backend live + Auth

•  Boot Laravel, run migrations, seed the mock data into the database.

•  Sanctum login / register / logout + token issuance.

•  React: replace the Landing “Enter” with a real login screen; store token; authed API client.

•  Define the API contract (Postman / OpenAPI) so Flutter can reuse it.

•  ✅ End of week: you can log in for real and hit a live API.

Week 2  ·  Jul 6 – Jul 12   —   Chat & Channels on real data

•  Wire channels + messages: list, send, persist (remove mock data for chat).

•  Reactions, message edit / delete, drafts (tables already exist).

•  Loading / empty / error states.

•  ✅ End of week: chat works across page reloads, stored in DB.

Week 3  ·  Jul 13 – Jul 19   —   Realtime + Tasks + Docs

•  WebSockets (Laravel Reverb or Pusher) → live messages + presence dots.

•  Kanban: task CRUD + drag-drop persistence.

•  Notion docs: block save / load.

•  Activity log feed in Admin.

•  ✅ End of week: two browsers see each other’s messages live; tasks/docs persist.

Week 4  ·  Jul 20 – Jul 26   —   AI + File Vault + Flutter wiring

•  Wire Gemini copilot (thread summaries, Cmd+K smart search) via GeminiController.

•  Vault uploads → Laravel storage + download.

•  Point the Flutter app at the same API (auth + chat + tasks reuse the contract).

•  Analytics fed by real aggregates instead of hard-coded numbers.

•  ✅ End of week: AI works, files upload, mobile app talks to the same backend.

Week 5  ·  Jul 27 – Jul 31   —   Polish, deploy, demo

•  Notifications + settings persistence, responsive / QA bug bash.

•  Deploy: backend (Railway / Forge) + web (Vercel / Netlify), build Flutter APK.

•  Seed a demo workspace, write README + short demo video.

•  ✅ End of week: shipped.

What you will have by 31 July

A working full-stack MVP of Flow:

•  Real auth (login / register, tokens)

•  Persistent chat with reactions + live realtime updates & presence

•  Docs, Kanban tasks, calendar — all backed by the database

•  Gemini AI copilot (summaries + smart search)

•  Working file vault (upload / download)

•  Analytics from real data

•  Deployed web app + installable Flutter build, sharing one backend

Realistic solo dev: this is an aggressive pace. If time slips, the safe cut line is — drop realtime (Week 3) to polling, and ship Flutter as “auth + chat only.” That still leaves a demoable product on 31 July.